**Community Standards Department Goals for 2013-2014**

|  |  |
| --- | --- |
|  | **Completion Deadline** |
| **CS: Recruit and train additional faculty members to serve on the University Hearing Panel and develop a plan for sustaining membership** | February 2014 |
| 1. Develop UHP recruitment, training, and retention schedule for current and subsequent academic years | October 2013 |
| 1. Prepare and send marketing/recruitment materials to all faculty | November 2013 |
| 1. Conduct mid-year and new academic year training workshops for members of Hearing Panel | January 2014 |
| **CS: Offer at least two student outreach/training programs each semester geared towards promoting conduct standards and/or civility, integrity, ethics** | March 2014 |
| 1. Hire a new coordinator of Community Standards in order to provide additional staff resources to conduct programs | December 2014 |
| 1. Review conduct violation and other assessment data to gauge needed targeted programming | January 2014 |
| 1. Plan, schedule, and implement educational programs | March 2014 |
| **HRLCS: In collaboration with Public Safety, plan and coordinate an emergency response exercise (tabletop or actual drill) and with other appropriate campus units** | January 2014 |
| 1. Department heads develop initial scope and planned outcomes for exercise | September 2013 |
| 1. Key department staff convene to develop/plan response exercise logistics | November 2013 |
| 1. Implement response exercise and include debriefing and evaluation | January 2014 |