**Housing and Residence Life Goals for 2013-2014**

|  |  |
| --- | --- |
|  | **Completion Deadline** |
| **HRL: Develop and implement a comprehensive assessment and evaluation plan for the expanded living/learning communities in Laker Hall** | March 2014 |
| 1. Charge existing L/LC committee with assessment and evaluation goals for 2013-14 and determine initial scope and plan
 | August 2013 |
| 1. Administer surveys and other assessment tools
 | January 2014 |
| 1. Compile and analyze data and prepare assessment results and report
 | February 2014 |
| **HRL: Explore and establish one new group housing options for a targeted student population (veterans, married, gender neutral, family, individual/single unit faculty, etc.)** | June 2014 |
| 1. Analyze theme housing trends
 | January 2014 |
| 1. Evaluate needs for campus populations
 | January 2014 |
| 1. Determine appropriate facility for potential new group housing location
 | January 2014 |
| 1. Plan, fund, and implement any needed structural modifications
 | April 2014 |
| 1. Develop and implement a strategic marketing and assignment plan for grouping theme
 | May 2014 |
| **HRL: Review and evaluate HRL website structure and redesign for more user-friendly and efficient access** | February 2014 |
| 1. Review current content and menu organization
 | December 2013 |
| 1. Develop plan and schedule for menu and content revisions
 | January 2013 |
| 1. Enlist office of Marketing and Communications for assistance in completing changes per schedule
 | February 2013 |
| **HRL: Develop a 2-year cycle for enhancing marketing and advertising materials** | March 2014 |
| 1. Collaborate with office of Marketing and Communications to determine housing marketing needs and strategies
 | October 2013 |
| 1. Develop marketing “refresh” plan based on key contracting dates; include content and photos augmentation
 | December 2013 |
| 1. Implement plan for design and production of materials
 | March 2014 |
| **HRLCS: In collaboration with Public Safety, plan and coordinate an emergency response exercise (tabletop or actual drill) and with other appropriate campus units** | January 2014 |
| 1. Department heads develop initial scope and planned outcomes for exercise
 | September 2013 |
| 1. Key department staff convene to develop/plan response exercise logistics
 | November 2013 |
| 1. Implement response exercise and include debriefing and evaluation
 | January 2014 |